## Tabelle1
[8 empty] | Sprint | Velocity | Avg
Sprint | Storypoints left | Done Storypoints | Assigned Storypoints | Expected |  |  |  | 1 | 18 | 18
0 | 195 | 0 | 0 | 195 | Storypoints Per Sprint: |  |  | 2
1 | 195 | 18 | 52 | 195 | 195 |  |  | 3
2 | 177 |  |  | 170.625 |  |  |  | 4
3 | 177 |  |  | 146.25 |  |  |  | 5
4 | 177 |  |  | 121.875 |  |  |  | 6
5 | 177 |  |  | 97.5 |  |  |  | 7
6 | 177 |  |  | 73.125 |  |  |  | 8
7 | 177 |  |  | 48.75 |  |  |  | 9
8 | 177 |  |  | 24.375
[5 empty] | Story name | StoryPoints
[5 empty] | Send/accept friend requests, to easier invite Friends to parties. | 21
[5 empty] | Lookup Location of friends | 31
[5 empty] | Add profile picture | 5
[5 empty] | Scan ticket QR Code | 8
[5 empty] | Add picture of party location | 5
[5 empty] | Get message when join request accepted | 13
[5 empty] | Lookup upcoming events and send request | 34
[5 empty] | Create Profile | 5
[5 empty] | Post a new Party/event | 34
[5 empty] | Receive message for new party request | 13
[5 empty] | Login/Register | 13 | Done
[5 empty] | Cancel Party | 13